## Slide 1
Migration Plan - Executive Summary
Level 1: one line per activity, key milestones
Activity | Type | Dev done | Tests done | Ready for migration | Go-live prep done | Total weeks
Complex1 | complex | 28-Feb-25 | 30-May-25 | 04-Jul-25 | 25-Jul-25 | 29
Complex2 | complex | 28-Feb-25 | 30-May-25 | 04-Jul-25 | 25-Jul-25 | 29
Simple1 | simple | 31-Jan-25 | 21-Feb-25 | 14-Mar-25 | 28-Mar-25 | 12
Simple2 | simple | 31-Jan-25 | 21-Feb-25 | 14-Mar-25 | 28-Mar-25 | 12
Simple3 | simple | 31-Jan-25 | 21-Feb-25 | 14-Mar-25 | 28-Mar-25 | 12
Simple4 | simple | 31-Jan-25 | 14-Mar-25 | 04-Apr-25 | 18-Apr-25 | 15

## Slide 2
Complex1 (complex) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
25-Jul-25
Development
SIT large @ ENV-A
SIT large @ ENV-A
SIT large @ ENV-A
E2E medium @ ENV-A
E2E medium @ ENV-A
Inflight order test
Application test
Go-live preparation
Ready for migration: 04-Jul-25 Go-live preparation complete: 25-Jul-25

## Slide 3
Complex2 (complex) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
25-Jul-25
Development
SIT large @ ENV-B
SIT large @ ENV-B
SIT large @ ENV-B
E2E medium @ ENV-B
E2E medium @ ENV-B
Inflight order test
Application test
Go-live preparation
Ready for migration: 04-Jul-25 Go-live preparation complete: 25-Jul-25

## Slide 4
Simple1 (simple) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
28-Mar-25
Development
SIT small @ ENV-A
SIT small @ ENV-A
E2E small @ ENV-A
Inflight order test
Application test
Go-live preparation
Ready for migration: 14-Mar-25 Go-live preparation complete: 28-Mar-25

## Slide 5
Simple2 (simple) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
28-Mar-25
Development
SIT small @ ENV-C
SIT small @ ENV-C
E2E small @ ENV-C
Inflight order test
Application test
Go-live preparation
Ready for migration: 14-Mar-25 Go-live preparation complete: 28-Mar-25

## Slide 6
Simple3 (simple) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
28-Mar-25
Development
SIT small @ ENV-D
SIT small @ ENV-D
E2E small @ ENV-D
Inflight order test
Application test
Go-live preparation
Ready for migration: 14-Mar-25 Go-live preparation complete: 28-Mar-25

## Slide 7
Simple4 (simple) - Detailed Plan
Level 2: phases and environment bookings
06-Jan-25
18-Apr-25
Development
SIT small @ ENV-A
SIT small @ ENV-C
E2E small @ ENV-C
Inflight order test
Application test
Go-live preparation
Ready for migration: 04-Apr-25 Go-live preparation complete: 18-Apr-25

## Slide 8
Environment Utilization
Level 3: days booked per environment
Environment | Capacity | Available from | Available to | Booked days
ENV-A | all | 06-Jan-25 | 31-Dec-25 | 85 (Complex1:65, Simple1:15, Simple4:5)
ENV-B | all | 03-Mar-25 | 31-Dec-25 | 65 (Complex2:65)
ENV-C | small | 06-Jan-25 | 30-Jun-25 | 25 (Simple2:15, Simple4:10)
ENV-D | small | 03-Feb-25 | 30-Sep-25 | 15 (Simple3:15)

## Slide 9
Planning Assumptions
Level 3: all parameter values used by the plan
Activity | Type | Dev (wk) | SIT runs | SIT size | E2E runs | E2E size | App test (wk) | Inflight (wk)
Simple1 | simple | 4 | 2 | small | 1 | small | 3 | 2
Simple2 | simple | 4 | 2 | small | 1 | small | 3 | 2
Simple3 | simple | 4 | 2 | small | 1 | small | 3 | 2
Simple4 | simple | 4 | 2 | small | 1 | small | 3 | 2
Complex1 | complex | 8 | 3 | large | 2 | medium | 5 | 4
Complex2 | complex | 8 | 3 | large | 2 | medium | 5 | 4
Test size | SIT days/run | E2E days/run
small | 5 | 5
medium | 10 | 10
large | 15 | 15
xlarge | 25 | 20
Environment | Capacity | Available from | Available to
ENV-A | all | 06-Jan-25 | 31-Dec-25
ENV-B | all | 03-Mar-25 | 31-Dec-25
ENV-C | small | 06-Jan-25 | 30-Jun-25
ENV-D | small | 03-Feb-25 | 30-Sep-25
Plan starts: 06-Jan-25 | Working days per week: 5
Per activity: Development -> SIT runs -> E2E runs -> Application test -> Go-live preparation are sequential.
Inflight order test runs in parallel with Application test (starts same day).
SIT and E2E runs book a capable, available environment for consecutive working days;
activities are scheduled in priority order: Complex1, Complex2, Simple1, Simple2, Simple3, Simple4.
Go-live preparation starts after readiness (max of application and inflight order tests).